## Evidence_Tracker
Control ID | Control Area | Control Description | Risk | Evidence Required | Evidence Received | Status | Finding | Severity | Owner | Target Date | Closure Date | Remarks
ITGC-001 | Access Control | User access review performed monthly | Unauthorized access | Access review report screenshot | Y | Completed | No | Low | IT Team | 2026-02-15 | 2026-02-12 | Completed successfully
ITGC-002 | Access Control | MFA enabled for admin accounts | Account compromise | MFA proof screenshot | N | Pending | - | High | Security Team | 2026-02-20 | - | Evidence not received
ITGC-003 | Backup | Daily backup performed and monitored | Data loss | Backup logs report | Y | In Progress | No | Medium | Infra Team | 2026-02-18 | - | Backup log review ongoing
ITGC-004 | Change Management | Change approvals required before deployment | Unauthorized changes | Change request approval document | Y | Completed | Yes | High | DevOps Team | 2026-02-10 | 2026-02-09 | 2 changes missing approval
ITGC-005 | Monitoring | System logs reviewed weekly | Threat undetected | Log monitoring report | N | Not Started | - | Medium | SOC Team | 2026-02-25 | - | Not initiated

## Dashboard
Total Controls | 5 | Status | Count | Severity | Count
Completed | 2 | Completed | 2 | Low | 1
Pending Evidence | 2 | Pending | 1 | Medium | 2
Findings | 1 | In Progress | 1 | High | 2
|  | Not Started | 1 | Critical | 0